**Achievement Accumulation of Agriculture Sector**

**For the end six month of the phase 1 (January to June, 2012)**

|  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| **No** | **Date** | **Activity** | **Beneficiary** | | **Material** | **Unit** | **Village** |
| Total | Female |
| 1 | On April, 2012 | Provided chicken cage and worm | 32 | 11 | 32 | cages | 16 |
| 2 | Provided on 29 June, 2012 | Provided livestock medecine | 41 | 7 | 41 | Package | 16 |
| 3 | Conducted on 14th to 15th February, 2012 | ToT AEA | 32 | 2 | - | - | 16 |
| 4 | Conducted 20th, 21st March, 9th & 10th, April, 2nd, 3rd, 7th, 8th, 16th, and 31st May and 7th June, 2012 | Dissemination on AEA | 486 | 387 | - | - | 16 |
| 5 | Done on 17th, 18th, 19th, 24th, January, 13th, 14th, 15th, 28th, February, 2012 | Mushroom growing dissemination |  |  | - | - | 8 |
| 6 | Done on 25th to 26th January, 2012 | ToT post harvest | 30 | 2 | - | - | 16 |
| 7 | Done on 13th, 14th, 15th, 16th, 28th, 29th, February, 1st, 6th, 7th, 12th, 26th, 27th, 28th, 29th March, 25th April 16th May 2012. | Post Harvest Dissemination | 439 | 335 | - | - | 16 |
| 8 | Done, conducted on 11th April, and 6th June, 2012. | FWUC meeting | 12 | 2 | - | - | - |

**Achievement Accumulation of Agriculture Sector**

**For the First six month of the phase 2 (2nd July to 31st Dec, 2012)**

|  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| **No** | **Date** | **Activity** | **Beneficiary** | | **Material** | **Unit** | **Village** |
| Total | Female |
| 1 | - | Joined Project Orientation | - | - | - | - | - |
| 2 | - | Joined for Baseline survey for whole processes | - | - | - | - | - |
| 3 | Conducted on 6th, 7th, 8th and 12th-Nov-12 | Promotion Choosing beneficiary for Agri- Sector | 337 | 432 | - | - | 7 |
| 4 | Conducted on 19th, 20th, 21st, and 27th-Nov-2012 | Ellection Choosing APGC and bylaw development | 302 | 200 | - | - | 7 |
| 5 | Conducted on 5th-6th, Dec 2012 | ToT AEA | 33 | 8 | - | - | 7 |
| 6 | Conducted on 22th-23th, Nov 2012 | Staff exposure trip for learning | 5 | 0 | - | - | - |
| 7 | Conducted on 20th-21st, Dec 2012 | APGC leader exposure trip for learning | 7 | 1 | - | - | 7 |
| 8 | Conducted on 27th-28th, Dec 2012 | ToT Composting and Soil preparation | 25 | 8 | - | - | 7 |
| 9 | Bought on 28st Dec, 2012 | Support materials for APG process |  |  | - | - | 7 |
| 10 | Bought on 28st Dec, 2012 | Support Material and vegetable seed for APG’s vegetable member who requested | 33 | 15 | - | - | 7 |

**Challenges Encountered, Solution has made and**

**Internal Strategy for Agriculture Sector**

|  |  |  |
| --- | --- | --- |
| **Challenge** | **Solution** | **Strategy** |
| 1. The target group has limited in adapting agriculture’s activity (animal raising, composting, vegetable growing...) because lacking of resource, lablour, or commitment/willingness | - Monitoring for motivation  - Support materials (Seed, Cage, medicine...)  - Family production trend  - Domonstration  - Exposure trip | - Identify root courses  - Compile the strategy to respond  - Trend to family production  - Continue and increase monitor to motivate  - Establish APG  - Rent specialized consultant for the needed tasks and un-clear for demo for staff capacity building  - Conduct regular meeting for APG  - Using rational agriculture technique  - Croose visit, exposure trip  - Distribution form project |
| 1. Assume the forsees failure from the beneficiary |  |  |
| 1. The time was shorter than the tasks scale |  |  |
| 1. Staff capacity was limited |  |  |
| 1. Cooperation of VDCs, CC and other key person is limited |  |  |
| 1. Activity review/reflection was poor performance. |  |  |
| 1. Agriculture’s and CD’s activity was almost and overllaped with the same target group |  |  |
| 1. Staff is un-clear on the process of the activity |  |  |